## Server Build Sheet
Sl No | Build Date: 28-08-2024
1 | Parent RITM | Child RITM | RITM Transition | VM Name | IP Address | Cluster |  | VCenter | Date | Status
2 | RITM4915753(Win Build) | RITM4925517 | RITM4935838 | WBGVSIMATICP001 | 10.6.64.55 | BGHADRS001 |  | WB5VC001 | 2024-08-28 | Completed
3 | RITM4926384(Linux Build)
4
5 | Build Date: 02-09-2024 | (Windows Build)
6 | DC | vCPU | vRAM | Storage | Parent RITM | Child Build RITM | Trasition RITM | CTASK | Project Name/Server Description | Hostname | C | D | Page | OS | Build Engineer | Build N/W | Status
7 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939377 | RITM4944198 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922072 | W6OVSNATMP001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
8 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939380 | RITM4944227 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922075 | W6OVSNATMP002 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
9 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939376 | RITM4944242 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922081 | W6OVSNATMS001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
10 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939374 | RITM4944249 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922086 | W6OVSNATMD001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
11
12 | Build Date: 02-09-2024 | (Linux Build)
13 | DC | vCPU | vRAM | Storage | IP Address | Cluster | Parent RITM | Child RITM | Transition RITM | project Name/Server Description | CTASK | Hosname | C | D | Page | OS | Build Engineer | N/W | Status
14 | 0B-GDC | 4 | 16 | 300 | 172.17.37.71 | 0BUAPPPRD001 | RITM4935184 | RITM4940342 | RITM4949251 | STOR management server | TASK0326044 | u0bvstormp01 | 120 | NA | 32 | RHEL 9.2 | Keshavamurti KV | Ent | Completed
15
16 | Build Date: 03-09-2024 | (Win22k Build)
17 | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Trasition RITM | Project Name/Server Description | Hostname | C | D | E | T | L | Pagedrive | Sign Date | IP Address | OS | Build Engineer | Build N/W | Status
18 | 23-BRISBANE | 4 | 16 | 352 | RITM4913807 | RITM4947723 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913800 | W23VDCCBMSD001 | 120 | 100 | 100 | 0 | 0 | 32 | 2024-09-03 | 10.6.49.247 | W2k22 | Keshavamurti KV | MFG | Closed
19 | 23-BRISBANE | 4 | 16 | 402 | RITM4913807 | RITM4947724 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913795 | W23VDCBMSDBD001 | 120 | 100 | 100 | 25 | 25 | 32 | 2024-09-03 | 10.6.49.248 | W2k22 | Keshavamurti KV | MFG | Closed
20
21 | Manual Build Windows 2k19 | 2024-09-11
22 | Cluster | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Build Verification task | Project Name/Server Description | OS | Hostname | C Drive | D Drive | Pagedrive | VLAN | IP Address | N/W | CI Creation RITM | Priv acc | autologoff | Ci Relationship | Firewall Port Open | Change Request | Status
23 | E7HADRS001 | E7-DAL | 4 | 16 | 252 | RITM4936056 | RITM4957831 | RITM4978786 | TASK0328641 | MES EIH server - E7 | WE2K19 STD | WE7VMESEIHP001 | 120 | 100 | 32 | E7-DVPG-PC-MES-1126 | 10.4.37.106 | MFG Build | RITM4963040 | RITM4964353 | RITM4964366 | RITM4964392 | RITM4963222 | CHG0169182 | Closed
24
25 | Manual Build Windows 2k22 | 2024-09-12
26 | Cluster | DC | vCPU | vRAM | Storage | RITM/Project ID | Child RITM | Transition RITM | Project Name/Server Description | OS | Hostname | C Drive | D Drive | E Drive | T_TempDrive | L_LogDrive | Additional Drive | Pagedrive | VLAN | IP Address | SQL | Build Engineer | Build N/W | Status
27 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 252 | RITM4942756 | RITM4964150 | RITM4969410 | Komarom - NexOn System Upgrade -App | W2K22 STD | W5DVNEXAPPP001 | 120 | 100 |  |  |  |  | 32 | 152 | 10.248.201.7 |  | Keshavamurti KV | ENT | Closed
28 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 584 | RITM4942756 | RITM4964149 | RITM4969420 | Komarom - NexOn System Upgrade -DB | W2K22 STD | W5DVNEXDBP001 | 120 | 100 | 200 | 50 | 50 |  | 32 | 154 | 10.248.203.7 | SQL19 STD | Keshavamurti KV | ENT | Closed
29
30 | Automation Build ENT N/W | 19-09-2024-24-09-2024 | DM-Sreeraj p | CI/Handover Owner:Ravishankar Sethuraman
| DC | Cluster | Vcenter | vCPU | vRAM | Storage | RITM | Child RITM/CI Owner | Build Verification | Trasition RITM | Project Name/Server Description | Hostname | IP Address | OS | C Drive | D Drive | Add | Page | Build Engineer | Status
31 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973722 | TASK0330635 | RITM4978170 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2--SVCRITM4915920 | W0BVTWS008 | 172.17.36.174 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
32 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973730 | TASK0330635 | RITM4978186 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915934 | W0BVTWS009 | 172.17.36.177 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
33 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973727 | TASK0330635 | RITM4978191 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915944 | W0BVTWRPTS003 | 172.17.36.178 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
34 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973729 | TASK0330635 | RITM4978195 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915961 | W0BVTWD001 | 172.17.36.183 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
35 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973723 | TASK0330635 | RITM4978197 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915973 | W0BVTWD002 | 172.17.36.184 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
36 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973720 | TASK0330635 | RITM4978199 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915982 | W0BVTWRPTD001 | 172.17.36.187 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
37
38 | Automatio MFG Buiid 25-10-2024 | DM-Sreeraj p
39 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Build Verification Task | Trasition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
40 | 6J-AURANGABAD | 6JHADRS003 | w6evc001 | 4 | 16 | 252 | RITM4920471 | RITM5031584 | TASK0338730 | RITM5035727 | MES Upgrade for Packaging eBR- New EIH server- SVCRITM4920462 | W6JVMESEIHP002 | 120 | 100 | 32 | 192.168.113.11 | W2K19 | Keshav | Closed
41
42 | New Esxi Builds for C6-DUBLIN projects 05th Nov 2024--Delivered on 18th Nov 2024 DELL R750 Model
43 | [5 empty] | IDRAC Default Creds: root/$3CuredW@ll! Esxi Default Creds: root/20Pme1esx!
44 |  |  |  |  | Closed Change Request
46 | Esxi Hostname | IDRAC IP Address | Esxi IP Address | VMotion IP Address |  | AD DNS TASK | Trasition RITM | Change Request for VM migration Closed
47 | Ec6rr7u02.myl.com | 10.243.94.76 | 10.243.94.79 | 10.243.93.101 | CHG0173549 | CTASK0549124 | RITM5074799 | CHG0174471
48 | Ec6rr7u04.myl.com | 10.243.94.77 | 10.243.94.80 | 10.243.93.102 | CHG0173553 | CTASK0549127 | RITM5074800 | CHG0174471
49 | Ec6rr7u06.myl.com | 10.243.94.78 | 10.243.94.81 | 10.243.93.103 | CHG0173554 | CTASK0549128 | RITM5074801 | CHG0174471
50
51 | Automation Build ENT N/W | 20-11-2024-21-11-2024 | DM-Sreeraj p | CI/Handover Owner:Siva Kumar Tandai
52 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
53 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078980 | RITM5085351 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924478 | W07VTWP013 | 120 | 100 | 64 | 172.26.145.14 | W2K22 | Keshav | Closed
54 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078974 | RITM5085354 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924484 | W07VTWP014 | 120 | 100 | 64 | 172.26.145.15 | W2K22 | Keshav | Closed
55 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078972 | RITM5085355 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924489 | W07VTWP015 | 120 | 100 | 64 | 172.26.145.153 | W2K22 | Keshav | Closed
56
57 | Automation Build MFG N/W | 22-11-2024-26-11-2024 | DM-Sreeraj p | CI/Handover Owner:Vibha Vallabh Env: QA server
58 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | N/A | N/A | N/A | Page | IP Address | OS | Build Engineer | Status
59 | 6O-IDC | 6OWAPPNPRD001 | 6ovcsa002 | 4 | 16 | 252 | RITM4915458 | RITM5054174 | RITM5088562 | Global - MES Core 3.0 (PharmaSuite 11.1 for MYMES Core Environment- SVCRITM4915420 | W6OVMESQ002 | 120 | 100 | 0 | 0 | 0 | 32 | 10.232.46.105 | W2K19 | Keshav | Closed
60 | 6O-IDC | 6OWAPPNPRD001 | 6ovcsa002 | 4 | 16 | 252 | RITM4915458 | RITM5054172 | RITM5088563 | Global - MES Core 3.0 (PharmaSuite 11.1 for MYMES Core Environment- SVCRITM4915438 | W6OVMESQ003 | 120 | 100 | 0 | 0 | 0 | 32 | 10.232.46.106 | W2K19 | Keshav | Closed
61
62 | Automation Build MFG N/W | 26-11-2024-29-11-2024 | DM-Meghashyam K | CI/Handover Owner:Ashutosh V Parab
63 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Build Verification | Project Name/Server Description | Hostname | C Drive | D Drive | N/A | N/A | N/A | N/A | Page | IP Address | OS | Build Engineer | Status | Description
64 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 544 | RITM4781610 | RITM5028712 | RITM5094803 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781572 | W6TVGDINPIOD001 | 120 | 120 | 120 |  | 120 | 0 | 64 | 10.6.32.66 | W2K19 | Keshav | Closed | Interface Node - Pi & OPC - Dev- Indore
65 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 684 | RITM4781610 | RITM5028711 | RITM5094804 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781586 | W6TVGDINPIOP002 | 120 | 250 | 250 |  |  | 0 | 64 | 10.6.32.68 | W2K19 | Keshav | Closed | Interface Node 2 - Pi & OPC - Production - Indore
66 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 1404 | RITM4781610 | RITM5028713 | RITM5094806 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781588 | W6TVGDSHFTP001 | 120 | 120 |  |  |  | 1100 | 64 | 10.6.32.69 | W2K19 | Keshav | Closed | FT Historian Server -Indore
68
69 | Automation Build ENT N/W | 28-11-2024-30-11-2024 | DM-Meghashyam K | CI/Handover Owner:Viral Shah
70 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
71 | 6J-AURANGABAD | 6JHADRS003 | w6evc001 | 4 | 16 | 302 | RITM5091816 | RITM5094383 | RITM5096559-Pending | TASK0345982 | KTLO - APAC - OSD/API Adhoc-Server for Canon Uniflow-SVCRITM5091815 | W6JVUNIFLOWP003 | 120 | 150 | 32 | 172.28.177.103 | W2K22 | Keshav | Closed
72
76
77 | Manually SRA Build Server(0B&07) | OS-Win 2K22
78 | Hostname | Change Request | Transition RITM
79 | W0BPVSRAP001 | CHG0175768
80 | W0BPVSRAP002 | CHG0175774
81 | W07PVSRADR001 | CHG0175777
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314

## Server Upgrade Sheet
Sl No | RITM4930961 - D2 - Scale up and Extend Usage for Additional Doc Types & Sites | 2024-09-16
1 | Hostname | Vcenter | Child RITM | Current Version | Target Version | Change Request
2 | W0BD216MIGD004 | w0bvc001 | RITM4958581 | 2016 | 2022 | CHG0169373
3 | W0BD216MIGD005 | w0bvc001 | RITM4958583 | 2016 | 2022 | CHG0169374
4 | W0BD216MIGD006 | w0bvc001 | RITM4958576 | 2016 | 2022 | CHG0169375
5 | w6vagiacltp001 | w6vvc001 | RITM4958572 | 2012 | 2022 | CHG0169383/CHG0169384
6
7 | W0BD216MIGD004 | CHG0169373 | 18-Sep-24(06 AM to 06 PM) | Completed
8 | W0BD216MIGD005 | CHG0169374
9 | W0BD216MIGD006 | CHG0169375
10 | W6VAGIACLTP001(w6vvc001.myl.com) | CHG0169383 | 2012-2019 | Completed | yet to start | Manually Upgrade
11 |  | CHG0169384 | 2019-2022
12
13 | 25-09-2024(10 AM - 10 PM)
14 | Parent RITM | Child RITM | RE: Intake ID - RITM4781454 - Mylan Canada Quality Control Lab Inventory Tracking Application 4 Server Builds -Signed off | Delivery Mgr: Meghashyam K M | Request Owner: Steve Lough, Abdul Shameem | OS-Version | Service Name
15 | RITM4918868 | RITM4966725 | W15myp001 | CHG0170100-Closed | I have been through all of the processes and performed a release to the server and everything is working.¦ Steve | 2019-2022 | Application Servers
16 | RITM4918868 | RITM4966731 | W15myp002 | CHG0170104-Closed |  | 2019-2022
17 | RITM4918868 | RITM4966733 | W15myp003 | CHG0170106-Closed |  | 2016-2022
18 | RITM4918868 | RITM4966728 | W0bmypwd001 | CHG0170101-Closed |  | 2016-2022
19 | RITM4922480 | RITM4969714 | w0bmypdbd001 | CHG0170102-Closed | Completed | 2016-2022 | DB Server
20
21 | 26-09-2024(10 AM- 10 PM)
22 | Parent RITM | Child RITM | D2 Dev Migration Servers OS upgrade | Delivery Mgr: Meghashyam K M | Request Owner: Janardhan Madhavarapu | OS-Version | Service Name
23 | RITM4930961 | RITM4958569 | W0BD216MIGD002 | CHG0170346 | Server and applications are running fine. Thanks and Regards, Komal Madan | 2016-2022 | Application Servers
24 | RITM4930961 | RITM4958567 | W0BD216MIGD007 | CHG0170350 |  | 2016-2022
25 | RITM4930961 | RITM4958565 | W0BD216MIGD008 | CHG0170351 |  | 2016-2022
26 | RITM4930961 | RITM4958584 | W0BD216MIGD009 | CHG0170352 |  | 2016-2022
27
32 | Intake on 04-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 09th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment
33 | Parent RITM | Child RITM | Hostname | Change Requests | Current version | Testing Servers
34 | RITM4930961 | RITM4958563 | W0BD216MIGT004 | CHG0171045 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | CHG0168951-OS Upgrade.. reference change.
35 | RITM4930961 | RITM4958571 | W0BD216MIGT005 | CHG0171046 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | For the OS Upgrade Task Steps:
36 | RITM4930961 | RITM4958560 | W0BD216MIGT006 | CHG0171047 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Open the Service Catalog.
37 | RITM4930961 | RITM4958575 | W0BD216MIGT007 | CHG0171048 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Select OS In-Place Upgrade (Windows).
38 | RITM4930961 | RITM4958561 | W0BD216MIGT008 | CHG0171049 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Fill in the required details: Vcenter name, Hostname, Downtime, ISO path, and OS name.
39 | RITM4930961 | RITM4958570 | W0BD216MIGT009 | CHG0171050 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Submit the request; this will generate an RITM with a Change Request number.
40 | [7 empty] | Please forward the RITM to the technical approver (Venu).Put the server in maintainance mood manually by maintainance schedules.
41 | Intake on 14-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 17th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment |  | For the OS Upgrade Task Steps:
42 | Parent RITM | Child RITM | Hostname | Change Requests | Current version |  |  | First, check the available space on the C drive; ensure there is a minimum of 35GB.
43 | RITM4930961 | RITM4958578 | W0BD216MIGD001 | CHG0171655 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | If there is insufficient space, clear any unwanted files.
44 | RITM4930961 | RITM4958577 | W0BD216MIGD003 | CHG0171659 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | Monitor the C request. Close the App and DB service tasks; snapshots will be taken care of automatically.
45 | RITM4930961 | RITM4958582 | W0BD216MIGT001 | CHG0171658 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Mount the ISO to the VM and start the upgrade process.(Automatically)
46 | RITM4930961 | RITM4958566 | W0BD216MIGT002 | CHG0171656 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Monitor the status in the VM through the LogView folder using Script1.
47 | RITM4930961 | RITM4958564 | W0BD216MIGT003 | CHG0171657 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Need to monitor the Change Request and Reuest Pending Change RITM's
48 | [7 empty] | Close the App and DB service CTasks.
49 | Intake on 05-Nov-2024 | DM: Shital N | RITM5083480- SAP_ End of Support Life (EOSL) W0BRTMP001 OS Upgrade ¦ Activity Scheduled on 16th Dec 2024 06.30 AM-2PM ¦ Requestor: Nisha Bhat
50 | Parent RITM | Child RITM | Hostname | Change Requests | Current version | Environment |  | Inform the server owner to start the application services and check the status.
51 | RITM5083480 | RITM5099388 | w0brtmp001 | CHG0176747 | Microsoft Windows Server 2012 R2 STD- 2022 STD | Jump Server | Need to remove snapshot manually | Attach the post-upgrade activity details, including: 1. Hostname and Properties, 2. Drive Details, 3. Screenshot
52 | [7 empty] | 1. Upgrade the VMware Tools.
53 | Hostname | OS | CTASK |  |  |  |  | 2. Change the hardware compatibility version to the latest version.
54 | w0brtmp001 | Microsoft Windows Server 2019 STD | CTASK0558062 |  |  |  |  | 3. Update the Guest OS version in the VMware Options console (OS Container).
55 | [7 empty] | 4. Inform the Patch team to push the latest updates.
56 | [7 empty] | 5. Uninstall the Carbon Black Agent from the old servers 2022 servers no need this agent.
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370

## C6-DUBLIN-Migration
Sl No
1 | C6 Cluster Migration Plan | DM: Senthinathan J
2 | C6HADRS003---> 001 &002 All VM's need to migrate from cluster 3 to 2&1
3 | and need to add all cluster 3 nodes to cluster 2
4
5 | C6-DUBLIN(4 Ports, 2MFG, 2ENT, 2FC) | Status/Remarks | Server IP
6 | C6HADRS001 | Only Cisco Servers
7 | ec6vm001.myl.com | IMM not reachable
8 | ec6vm002.myl.com | IMM not reachable
9 | ec6vm003.myl.com | UP & Reachable | 10.243.94.100
10 | ec6vm004.myl.com | IMM not reachable |  | Change for Boot Lun Migration: CHG0176742
11 |  |  |  | root
12 | C6HADRS002 | Status/Remarks | Only DELL servers IP | $3CuredW@ll!
13 | ec6rr0u11.myl.com | IDRAC UP & Reachable | 10.243.94.15 | Esxi Default Creds: root/
14 | ec6rr0u13.myl.com | IDRAC UP & Reachable | 10.243.94.16 | 20Pme1esx!/20pme1esx!/20pme1esx | C6-DUBLIN Location DELL Serevers
15 | ec6rr0u15.myl.com | IDRAC UP & Reachable | 10.243.94.17 |  | Sl.No | Make & Model | Serial Number | Hostname | IP Address | Remarks/Status
16 | ec6rr0u17.myl.com | IDRAC UP & Reachable | 10.243.94.18 |  | 1 | DELL PowerEdge R740 | F31SYP3 | ec6rr0u11.myl.com | 10.243.94.15 | Server UP, Esxi 8.0.3 Installed, IP, Hostname configured, need to add to the cluster, DATA ports are showing Not Supported
17 | ec6rr0u19.myl.com | IDRAC UP & Reachable | 10.243.94.19 |  | 2 | DELL PowerEdge R740 | G31SYP3 | ec6rr0u13.myl.com | 10.243.94.16 | Server UP, Esxi 8.0.3 Installed, IP, Hostname configured, need to add to the cluster
18 |  |  |  |  | 3 | DELL PowerEdge R740 | H31SYP3 | ec6rr0u15.myl.com | 10.243.94.17 | Server UP, Esxi 8.0.3 Installed, IP, Hostname configured, need to add to the cluster
19 | C6HADRS003 | Status/Remarks |  |  | 4 | DELL PowerEdge R740 | J31SYP3 | ec6rr0u17.myl.com | 10.243.94.18 | Server UP, Esxi 8.0.3 Installed, IP, Hostname configured, need to add to the cluster
20 | ec6rr7u02.myl.com | IDRAC UP & Reachable |  |  | 5 | DELL PowerEdge R740 | 141SYP3 | ec6rr0u19.myl.com | 10.243.94.19 | Server UP, Esxi 8.0.3 Installed, IP, Hostname configured, need to add to the cluster
21 | ec6rr7u04.myl.com | IDRAC UP & Reachable
22 | ec6rr7u06.myl.com | IDRAC UP & Reachable
23
Sl.No | Hostname | IDRAC IP Address | WWPN1 | WWPN2
1 | ec6vm001.myl.com |  | IMM not reachable
2 | ec6vm002.myl.com |  | IMM not reachable
3 | ec6vm003.myl.com |  | UP & Reachable
4 | ec6vm004.myl.com |  | IMM not reachable
5 | ec6rr0u11.myl.com |  | 21:00:F4:C7:AA:08:05:6D | 21:00:F4:C7:AA:08:04:CD
6 | ec6rr0u13.myl.com |  | 21:00:F4:C7:AA:08:06:07 | 21:00:F4:C7:AA:08:04:D7
7 | ec6rr0u15.myl.com |  | 21:00:F4:C7:AA:08:05:6F | 21:00:F4:C7:AA:08:05:0B
8 | ec6rr0u17.myl.com |  | 21:00:F4:C7:AA:08:04:E1 | 21:00:F4:C7:AA:08:05:2D
9 | ec6rr0u19.myl.com |  | 21:00:F4:C7:AA:08:04:D3 | 21:00:F4:C7:AA:08:05:0F
Sl.No | Hostname | WWPN1 | WWPN2
1 | ec6rr0u11.myl.com | 21:00:F4:C7:AA:08:05:6D | 21:00:F4:C7:AA:08:04:CD
2 | ec6rr0u13.myl.com | 21:00:F4:C7:AA:08:06:07 | 21:00:F4:C7:AA:08:04:D7
3 | ec6rr0u15.myl.com | 21:00:F4:C7:AA:08:05:6F | 21:00:F4:C7:AA:08:05:0B
4 | ec6rr0u17.myl.com | 21:00:F4:C7:AA:08:04:E1 | 21:00:F4:C7:AA:08:05:2D
5 | ec6rr0u19.myl.com | 21:00:F4:C7:AA:08:04:D3 | 21:00:F4:C7:AA:08:05:0F

## SRA & Trackwise Srvs
Sl.no | Site Code | Location | Make | Model | Qty | Project | OS | Remarks | Priorty | ETA |  | IDRAC IP DETAILS
1 | 0B | GDC, Ashburn | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 1 | 30th Nov | W0BPVSRAP001-IMM | 172.17.70.18 | 255.255.255.0 | 172.17.70.1
2 | 0B | GDC, Ashburn | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 2 | 6th Dec | W0BPVSRAP002-IMM | 172.17.70.19 | 255.255.255.0 | 172.17.70.1
| 0'7 | MGW | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 1 |  |  | 172.31.0.15
3 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | Sandbox infra, Boot via Storage | 1 | 30th Nov | u0bptwisdbs03-IMM | 172.17.70.164 | 255.255.255.0 | 172.17.70.1
4 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | Near DR infra, Boot via Storage | 3 | 9th Dec | u0bptwisdbp03-IMM | 172.17.70.165 | 255.255.255.0 | 172.17.70.1
5 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | PROD Infra, Boot via Stroage | 3 | 9th Dec | u0bptwisdbn03-IMM | 172.17.70.166 | 255.255.255.0 | 172.17.70.1
1 | 0'7 | MGW | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain
2 | 0'7 | MGW | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | DR, Boot via Storage | 2 | 6th Dec | u07ptwisdbf03-IMM | 172.31.0.16 | 255.255.255.128 | 172.31.0.1
IDRAC Creds:
| root |  | Trackwise servers RHEL 8.8
| Vi@tris2024 |  | Boot LUN RITM:RITM5099499
Boot LUN RITM:RITM5099702
1 | u0bptwisdbs03 | fc10/46 500 0x9406a0 10:00:70:b7:e4:21:b8:18 20:00:70:b7:e4:21:b8:18
fc10/46 600 0x1d0900 10:00:70:b7:e4:21:b8:19 20:00:70:b7:e4:21:b8:19
2 | u0bptwisdbp03
3 | u0bptwisdbn03
4 | u07ptwisdbf03

## EXP
Sl.No | Oct 2024 Expense | INR | Status | Remarks |  | Sl.No | Dec 2024 Expense | INR | Status | Remarks
1 | Ration | 3740 | Done |  |  | 1 | Ration | 3000 | Done
2 | House Rent | 12500 | Done | 4k cash remains |  | 2 | House Rent | 13384 | Done | 6500/- rcvd.
3 | Car Loan | 17666 | Done |  |  | 3 | Car Loan | 17666 | Done
4 | Mutual Fund | 14000 | Done |  |  | 4 | Mutual Fund | 14000+7000(Kuvera App) | Done
5 | Metro Recharge | 900 | Done |  |  | 5 | Metro Recharge | 800 | Done
6 | Credit card | 2500 | Done |  |  | 6 | Credit card Bill | 1500 | Done
7 | Medicine | 1200 | Done |  |  | 7 | Moved to SBI | 10000 | Done
8 | Bglkt Expense on 9th Oct | 5500 | Done |  |  | 8 | Suzlon&TATA steel stocks | 5500 | Done
9 | Moved to SBI | 20000 | Done |  |  | 9 | Gold Ring Confirmed | 2000 | Done | 2k Advance Given=22k yet to pay
10 | Scooty Petrol | 1000 |  |  |  | 10 | Medicine & scooty Petrols, car petrol | 4200 |  |  | 300=drinks sat night
11 | Total | 75266 |  |  |  | 11 | Total | 58050 |  |  | 225+868=sun nigth
12 | Salary | 100301 |  |  |  | 12 | Balance | 32,574(HDFC), 85,202(SBI)
13 | Exp | 49766
14 | Balance | 50635
Sl.No | Nov 2024 Expense | INR | Status | Remarks
1 | Ration | 4500 | Done
2 | House Rent | 13500 | Done | 6300 cash given by venkatesh
3 | Car Loan | 17666 | Done
4 | Mutual Fund | 14000 | Done
5 | Metro Recharge | 1000 | Done
6 | Bike Trip | 3000 | Done
7 | Moved to SBI | 30000 | Done
8 | Scooty Petrol | 1000 | Done
9 | Total | 84666
10 | Balance | 100301
Wayanad Trip Exp
| 1000 | Fast Tag |  |  | Car Mileage Details
| 875 | Waynad checkpost Lunch |  |  | total petrol | 5610 | 54ltr
| 200 | Snacks |  |  | Km | 646 | 170-pending
| 350 | Ice Cream
| 1500 | Car Petrol
3925