## Final Rack Layout
DAMASTOWN MDF - IT RACK ELEVATION
|  | LAN Rack |  |  | Cable Mgmt Patch panels |  |  | Network 1 |  |  | Network 2 |  |  | Platform 1 |  |  | Platform 2 |  |  | Backup (TBC) | [9 empty] | EVOLUTION ACCESS CONTROL & CCTV
| New Server Room - Rack 10 |  |  | New Server Room - Rack 09 |  |  | New Server Room - Rack 08 |  |  | New Server Room - Rack 07 |  |  | New Server Room - Rack 06 |  |  | New Server Room - Rack 05 |  |  | New Server Room - Rack 04 |  |  | New Server Room - Rack 03 |  | New Server Room - Rack 02 | Power Ports | Power Load | RACKED DEVICES IN GREEN |  | New Server Room - Rack 01 |  | Power Load | RACKED DEVICES IN GREEN
[25 empty] | 44 | 10180 | NOT YET ON SITE |  |  |  | 10180 | NOT YET ON SITE
42 |  |  | 42 |  | MDF to IDF Fiber Jack Pannel 12 Port | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  | 42 |  |  |  |  | 42 |  | Tyco Power supply A
41 |  |  | 41 |  | Mezz Fiber Jack Panel 12 Port | 41 |  | AT&T - MUX | 41 |  | COLT - MUX | 41 |  |  | 41 |  |  | 41 |  |  | 41 |  | 41 |  |  |  |  | 41
40 |  |  | 40 |  | Comms 2 Fiber Jack Panel 12 Port | 40 |  |  | 40 |  |  | 40 |  |  | 40 |  |  | 40 |  |  | 40 |  | 40 |  |  |  |  | 40
39 |  |  | 39 |  | Cab F (Area 1) & Cab G (Area 2 Fiber Jack Panel 12 Port | 39 |  |  | 39 |  |  | 39 |  | SAN- SW1 Cisco DS-C9148T-K9 | 39 |  | SAN - SW 2 Cisco DS-C9148T-K9 | 39 |  |  | 39 |  | 39 |  | 2 | 350 |  | 39 |  | Tyco Power supply B | 350
38 |  |  | 38 |  | Dev/Cab E (Projects Office/Cab C (Warehouse) Fiber Panel 18 Port | 38 |  |  | 38 |  |  | 38 |  |  | 38 |  |  | 38 |  |  | 38 |  | 38 |  |  |  |  | 38
37 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 37 |  | 37 |  | 2 | 350 |  | 37 |  |  | 350
36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  | 36 |  |  |  | SERIAL NUMBERS | 36 |  | iStar Ultra CGM |  | SERIAL NUMBERS
35 |  |  | 35 |  |  | 35 |  |  | 35 |  |  | 35 |  |  | 35 |  |  | 35 |  |  | 35 |  | 35 |  | 1 | 160 | NOT ON SITE | 35 |  |  | 160 | NOT ON SITE
34 |  |  | 34 |  |  | 34 |  | IRE-C6DUB-MGMT-SW1 - FOC2820Y2PA | 34 |  |  | 34 |  | uc6pnbmep001-CZ212107MH | 34 |  | DELl PowerEdge R740 - uc6pnbmep003 | 34 |  |  | 34 |  | 34 |  | 1 | 160 | CR0026985 | 34 |  | iStar Ultra ACM | 160 | CR0026985
33 |  |  | 33 |  | Cat6 Panel 24 Port | 33 |  |  | 33 |  |  | 33 |  |  | 33 |  |  | 33 |  |  | 33 |  | 33 |  | 2 | 240 | 11901039336 | 33 |  |  | 240 | 11901039336
32 |  |  | 32 |  | cable Management | 32 |  | IRE-C6DUB-CONSOLE-SW1 | 32 |  | IRE-C6DUB-IB - 805201705700209 | 32 |  |  | 32 |  |  | 32 |  |  | 32 |  | 32 |  | 2 | 240 | 11901041391 | 32 |  |  | 240 | 11901041391
31 |  |  | 31 |  | Cat6 Panel 24 Port | 31 |  |  | 31 |  |  | 31 |  |  | 31 |  |  | 31 |  |  | 31 |  | 31 |  | 2 | 550 | TW13KM004L | 31 |  |  | 550 | TW13KM004L
30 |  |  | 30 |  | cable Management | 30 |  | IRE-C6DUB-WAN-RTR1 - FCZ2801R2CB | 30 |  | IRE-C6DUB-WAN-RTR2 - FCZ2624R7J4 | 30 |  | NetApp FAS 8300 - Disk Shelf (NC6CLST002) | 30 |  | Dell DD3300 SC6DD001 | 30 |  |  | 30 |  | 30 |  | 2 | 550 | TW13KM004T | 30 |  | iStar Ultra ACM | 550 | TW13KM004T
29 |  |  | 29 |  | Cat6 Panel 24 Port | 29 |  |  | 29 |  |  | 29 |  |  | 29 |  |  | 29 |  |  | 29 |  | 29 |  | 2 | 550 | TW11KM0077 | 29 |  |  | 550 | TW11KM0077
28 |  |  | 28 |  | cable Management | 28 |  |  | 28 |  |  | 28 |  | NetApp FAS 8300 - Disk Shelf (NC6CLST002) | 28 |  |  | 28 |  |  | 28 |  | 28 |  | 2 | 550 | TW11KM0069 | 28 |  |  | 550 | TW11KM0069
27 |  |  | 27 |  | Cat6 Panel 24 Port | 27 |  | IRE-C6DUB-WLC1 - FCL27450021 | 27 |  | IRE-C6DUB-WLC2- FCL2745007V | 27 |  |  | 27 |  |  | 27 |  |  | 27 |  | 27 |  | 2 | 200 | SG12KN00Z8 | 27 |  |  | 200 | SG12KN00Z8
26 |  |  | 26 |  | cable Management | 26 |  |  | 26 |  |  | 26 |  | NetApp FAS 8300 - (NC6CLST002) | 26 |  |  | 26 |  |  | 26 |  | 26 |  | 2 | 200 | SG12KN00Z7 | 26 |  | Planet CCTV Switch | 200 | SG12KN00Z7
25 |  |  | 25 |  | Cat6 Panel 24 Port | 25 |  |  | 25 |  |  | 25 |  |  | 25 |  | UC6MEDIA001- WZP22351B6L | 25 |  |  | 25 |  | 25 |  |  |  |  | 25 |  | Blank
24 |  |  | 24 |  | cable Management | 24 |  | IRE-C6DUB-DIST-SW1 - FCW2336A169 | 24 |  | IRE-C6DUB-DIST-SW2 - FCW2336A13Y | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  | 24 |  |  |  |  | 24 |  | Blank
23 |  |  | 23 |  | Cat6 Panel 24 Port | 23 |  |  | 23 |  |  | 23 |  | EC6VM002 - WZP22351B6S | 23 |  | EC6VM004 - WZP234215YY | 23 |  |  | 23 |  | 23 |  |  |  |  | 23 |  | Video Edge CCTV
22 |  |  | 22 |  | cable Management | 22 |  | IRE-C6DUBL-MFG-FW - 01620104110 | 22 |  | IRE-C6DUBL-MFG-F - 013201041413 | 22 |  |  | 22 |  |  | 22 |  |  | 22 |  | 22 |  |  |  |  | 22 |  | Blank
21 |  | IRE-C6DUB-MFG-COM1-SW1(FOC2820Y2Q7) | 21 |  | Cat6 Panel 24 Port | 21 |  |  | 21 |  |  | 21 |  | EC6VM001 - WZP22351B6D | 21 |  | EC6VM003 - WZP234215Z3 | 21 |  |  | 21 |  | 21 |  |  |  |  | 21 |  | Blank
20 |  | Cable Manager | 20 |  | cable Management | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  | 20 |  |  |  |  | 20 |  | Blank
19 |  |  | 19 |  | Cat6 Panel 24 Port | 19 |  | IRE-C6DUB-MFG-DIST-SW1 - FDO2823108W | 19 |  | IRE-C6DUB-MFG-DIST-SW1 - FDO282516A0 | 19 |  | ec6rr0u19 - F31SYP3 | 19 |  |  | 19 |  |  | 19 |  | 19 |  |  |  | SGH124WGCR | 19 |  | Blank |  | SGH124WGCR
18 |  | IRE-DUB-C6-LAN-SW1(FDO2136E1L3) | 18 |  | cable Management | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  | 18 |  | 2 | 620 | SGH124WGCM | 18 |  | Blank | 620 | SGH124WGCM
17 |  | IRE-DUB-C6-LAN-SW1-2(FDO2202I1LC) | 17 |  | Cat6 Panel 24 Port | 17 |  | IRE-DUB-C6-MES-SW1 - FOC2820Y2PS | 17 |  |  | 17 |  | ec6rr0u17- G31SYP3 | 17 |  |  | 17 |  |  | 17 |  | 17 |  | 2 | 620 | SGH124WGCP | 17 |  | Blank | 620 | SGH124WGCP
16 |  | Cable Manager | 16 |  | cable Management | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  |  | 16 |  | 16 |  | 2 | 620 | SGH124WGCT | 16 |  | Blank | 620 | SGH124WGCT
15 |  |  | 15 |  | Cat6 Panel 24 Port | 15 |  |  | 15 |  |  | 15 |  | PowerEdge R750 Server - NEW | 15 |  | ec6rr0u15 - H31SYP3 | 15 |  |  | 15 |  | 15 |  | 2 | 620 | SGH110SJFV | 15 |  | Blank | 620 | SGH110SJFV
14 |  | IRE-DUB-C6-LAN-SW1-3(FDO2038E1MJ) | 14 |  | cable Management | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  |  | 14 |  | 14 |  | 2 | 620 | SGH110SJFS | 14 |  | Blank | 620 | SGH110SJFS
13 |  | IRE-DUB-C6-LAN-SW1-4(FDO2041E2UJ) | 13 |  | Cat6 Panel 24 Port | 13 |  |  | 13 |  |  | 13 |  | PowerEdge R750 Server - NEW | 13 |  | ec6rr0u13 - J31SYP3 | 13 |  |  | 13 |  | 13 |  | 2 | 620 | SGH110SJ3J | 13 |  | Static Switch | 620 | SGH110SJ3J
12 |  | Cable Manager | 12 |  | cable Management | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  |  | 12 |  | 12 |  | 2 | 320 |  | 12 |  | Blank | 320
11 |  |  | 11 |  | Cat6 Panel 24 Port | 11 |  |  | 11 |  |  | 11 |  |  | 11 |  | ec6rr0u11 - 141SYP3 | 11 |  |  | 11 |  | 11 |  | 2 | 320 |  | 11 |  | Blank | 320
10 |  | IRE-DUB-C6-LAN-SW8(FDO1838E0WD) | 10 |  | cable Management | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  | 10 |  | 2 |  |  | 10 |  | Blank
9 |  | IRE-DUB-C6-LAN-SW10(FDO2010E2H1) | 9 |  | Cat6 Panel 24 Port | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  | PowerEdge R750 Server - NEW | 9 |  |  | 9 |  | 9 |  |  |  | GH22NF3 | 9 |  | Blank |  | GH22NF3
8 |  | Cable Manager | 8 |  | cable Management | 8 |  |  | 8 |  |  | 8 |  | NetApp AFF-C250 - Disk Shelf | 8 |  |  | 8 |  |  | 8 |  | 8 |  | 2 | 750 |  | 8 |  | Blank | 750
7 |  |  | 7 |  | Cat6 Panel 24 Port | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  |  | 7 |  | 7 |  |  |  |  | 7 |  | Blank
6 |  | IRE-DUB-C6-LAN-SW11(FDO2017E2C9) | 6 |  | cable Management | 6 |  |  | 6 |  |  | 6 |  | NetApp AFF-C250 - Disk Shelf | 6 |  |  | 6 |  |  | 6 |  | 6 |  |  |  |  | 6 |  | Blank
5 |  | IRE-C6DUB-MFG-DEMING-SW1(FOC2603YLGB) | 5 |  | Cat6 Panel 24 Port | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 5 |  | 5 |  |  |  |  | 5 |  | Blank
4 |  | Cable Manager | 4 |  | cable Management | 4 |  |  | 4 |  |  | 4 |  | NetApp AFF-C250 | 4 |  |  | 4 |  |  | 4 |  | 4 |  | 2 | 970 | CRK00211200007 | 4 |  | Blank | 970 | CRK00211200007
3 |  |  | 3 |  | Cat6 Panel 24 Port | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  | 3 |  |  |  |  | 3 |  | Blank
2 |  |  | 2 |  | cable Management | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | 2 |  |  |  |  | 2 |  | Blank
1 |  |  | 1 |  | Cat6 Panel 24 Port | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  |  | 1 |  | Blank

## Device placements
S/N | Source Server Room ( Old Server Room) | [5 empty] | Destination
| Rack Name | U Number | Serial Number | Device Name | Movement Scope | Remarks | Rack Name | RU | Serial Number | Device Name | Site IT Remarks
1 | COMMS ROOM 1 RACK-1 | 42 |  | Cable Run | No
2 | COMMS ROOM 1 RACK-1 | 41 |  | Avigilon CCTV | No
3 | COMMS ROOM 1 RACK-1 | 40 |  | Avigilon CCTV | No
4 | COMMS ROOM 1 RACK-1 | 39 |  | Avigilon CCTV | No
5 | COMMS ROOM 1 RACK-1 | 38 |  | Fiber Patch Panel | No
6 | COMMS ROOM 1 RACK-1 | 37 |  | Cable Run | No
7 | COMMS ROOM 1 RACK-1 | 36 |  | ECI PG-20C_AC | No
8 | COMMS ROOM 1 RACK-1 | 35 |  | Cable Run | No
9 | COMMS ROOM 1 RACK-1 | 33, 34 | CZ212107MH | uc6pnbmep001 | Yes | Movement AS-IS | Platform 1, New Server Room - Rack 06 | 33,34 | CZ212107MH | uc6pnbmep001 | Physical Verification needed
10 | COMMS ROOM 1 RACK-1 | 31, 32 | WZP22351B6L | UC6MEDIA001 | Yes | Movement AS-IS | Platform 2, New Server Room - Rack 05 | 24, 25 | WZP22351B6L | UC6MEDIA001 | Physical Verification needed
11 | COMMS ROOM 1 RACK-1 | 29, 30 | WZP22351B6D | EC6VM001 | Yes | post observation | Platform 1, New Server Room - Rack 06 | 20, 21 | WZP22351B6D | EC6VM001 | Physical Verification needed
12 | COMMS ROOM 1 RACK-1 | 27, 28 | WZP22351B6S | EC6VM002 | Yes | post observation | Platform 1, New Server Room - Rack 06 | 22, 23 | WZP22351B6S | EC6VM002 | Physical Verification needed
13 | COMMS ROOM 1 RACK-1 | 25, 26 | WZP234215YY | EC6VM004 | Yes | post observation | Platform 2, New Server Room - Rack 05 | 22, 23 | WZP234215YY | EC6VM004 | Physical Verification needed
14 | COMMS ROOM 1 RACK-1 | 23, 24 | WZP234215Z3 | EC6VM003 | Yes | post observation | Platform 2, New Server Room - Rack 05 | 20, 21 | WZP234215Z3 | EC6VM003 | Physical Verification needed
15 | COMMS ROOM 1 RACK-1 | 22 |  | Eircom Fiber Panel | No | Mux
16 | COMMS ROOM 1 RACK-1 | 21 |  | ETX-205A - SEA512105011 | No | Mux
17 | COMMS ROOM 1 RACK-1 | 20 |  | Cable Run | No
18 | COMMS ROOM 1 RACK-1 | 19 |  | Patch Panel 1U | No
19 | COMMS ROOM 1 RACK-1 | 18 |  | BT ADVA | No | Mux
20 | COMMS ROOM 1 RACK-1 | 17 |  | Cable Tidy Panel 1U | No
21 | COMMS ROOM 1 RACK-1 | 16 |  | Colt Accedian NID | No | Mux
22 | COMMS ROOM 1 RACK-1 | 15 |  | Empty | No
23 | COMMS ROOM 1 RACK-1 | 14 |  | Cable Run | No
24 | COMMS ROOM 1 RACK-1 | 13 |  | Empty | No
25 | COMMS ROOM 1 RACK-1 | 11, 12 |  | NC6CLST001 - FAS 2650 (Controller) nC6clst001, 621848000016 & 621848000017 | No | will be retired
26 | COMMS ROOM 1 RACK-1 | 9, 10 |  | NETAPP Storage 224C (Disk Shelf) | No | will be retired
27 | COMMS ROOM 1 RACK-1 | 8 |  | Cable Run | No
28 | COMMS ROOM 1 RACK-1 | 7 | JAE18250BZ5 | IRE-C6DUB-MFG-DIST-SW1-01 | No | Replacement | Network 1, New Server Room - Rack 08 | 24 | FDO2823108W | IRE-C6DUB-MFG-DIST-SW1
29 | COMMS ROOM 1 RACK-1 | 6 | JAE1850026S | IRE-C6DUB-MFG-DIST-SW1-02 | No | Replacement | Network 2, New Server Room - Rack 07 | 24 | FDO282516A0 | IRE-C6DUB-MFG-DIST-SW2
30 | COMMS ROOM 1 RACK-1 | 5 |  | External Line Fiber Panel | No | Mux
31 | COMMS ROOM 1 RACK-1 | 4 |  | Empty/Cable Run | No
32 | COMMS ROOM 1 RACK-1 | 3 |  | Empty/Cable Run | No
33 | COMMS ROOM 1 RACK-1 | 2 |  | Empty/Cable Run | No
34 | COMMS ROOM 1 RACK-1 | 1 |  | Empty/Cable Run | No
35 | COMMS ROOM 1, RACK-2 | 42 |  | Cable Run | No
36 | COMMS ROOM 1, RACK-2 | 41 |  | Arista 7050T-64 48 | No | Retired & Disposed
37 | COMMS ROOM 1, RACK-2 | 40 |  | Cable Tidy Panel 1U | No
38 | COMMS ROOM 1, RACK-2 | 39 |  | Arista 7050T-64 48 | No | Retired & Disposed
39 | COMMS ROOM 1, RACK-2 | 38 |  | Cable Run | No
40 | COMMS ROOM 1, RACK-2 | 37 |  | ROTTAPRIESX1 | No | Retained till q1-2025
41 | COMMS ROOM 1, RACK-2 | 36 |  | ROTTAPRIESX2 | No | Retained till q1-2025
42 | COMMS ROOM 1, RACK-2 | 35 |  | ROTTAPRIESX3 | No | Retained till q1-2025
43 | COMMS ROOM 1, RACK-2 | 34 |  | ROTTAPRIESX4 | No | Retained till q1-2025
44 | COMMS ROOM 1, RACK-2 | 33 |  | ROTTAPRIESX5 | No | Retained till q1-2025
45 | COMMS ROOM 1, RACK-2 | 32 |  | RottaVeeamPrxy | No | Retained till q1-2025
46 | COMMS ROOM 1, RACK-2 | 31 | FDO2243A0GL | IRE-DUB-C6-WAN-RTR1 | Yes | Once ISP ready | Network 1, New Server Room - Rack 08 | 30 | FCZ2801R2CB | IRE-C6DUB-WAN-RTR1 | Physical Verification needed
47 | COMMS ROOM 1, RACK-2 | 30 |  |  | No
48 | COMMS ROOM 1, RACK-2 | 29 |  | Dell Powervault MD3220 | No | Retained till q1-2025
49 | COMMS ROOM 1, RACK-2 | 28 |  |  | No
50 | COMMS ROOM 1, RACK-2 | 27 |  | RottadubDC02 | No | Retained till q1-2025
51 | COMMS ROOM 1, RACK-2 | 26 | FCZ2624R7J4 | IRE-C6DUB-WAN-RTR2 | Yes | Once ISP ready | Network 2, New Server Room - Rack 07 | 30 | FCZ2624R7J4 | IRE-C6DUB-WAN-RTR2 | Physical Verification needed
52 | COMMS ROOM 1, RACK-2 | 25 |  |  | No
53 | COMMS ROOM 1, RACK-2 | 24 |  |  | No
54 | COMMS ROOM 1, RACK-2 | 23 |  | Dell KVM | No | Retained till q1-2025
55 | COMMS ROOM 1, RACK-2 | 21, 22 |  | RottaNAS03 | No | Retained till q1-2025
56 | COMMS ROOM 1, RACK-2 | 20 | FCW2244M096, FCW2244M08V | IRE-DUB-C6-WLC1, | No | replacement | Rack 8 & Rack 7 | 27 & 27 | FCL27450021/FCL2745007V | IRE-C6DUB-WLC1, IRE-C6DUB-WLC2
57 | COMMS ROOM 1, RACK-2 | 19 | FDO1838E0XA | IRE-DUB-C6-MES-SW1 | Yes | Movement AS-IS | Network 1, New Server Room - Rack 08 | 17 | FDO1838E0XA | IRE-DUB-C6-MES-SW1 | Physical Verification needed
58 | COMMS ROOM 1, RACK-2 | 18 |  | Firewall |  |  | Rack 8 | 22
59 | COMMS ROOM 1, RACK-2 | 17 |  | Firewall |  |  | Rack 7 | 22
60 | COMMS ROOM 1, RACK-2 | 16 | JAE200609P4 | IRE-DUB-C6-DIST-SW1-1 | No | replacement | Rack 8 | 24 | FCW2336A169 | IRE-C6DUB-DIST-SW1
61 | COMMS ROOM 1, RACK-2 | 15 | JAE195306XH | IRE-DUB-C6-DIST-SW1-2 | No | replacement | Rack 7 | 24 | FCW2336A13Y | IRE-C6DUB-DIST-SW2
62 | COMMS ROOM 1, RACK-2 | 10 to 14 |  | Dell Unity Server | No | Retained till q1-2025
63 | COMMS ROOM 1, RACK-2 | 9 |  | Empty | No
64 | COMMS ROOM 1, RACK-2 | 7, 8 |  | CCTV NVR | No
65 | COMMS ROOM 1, RACK-2 | 6 |  | Empty | No
66 | COMMS ROOM 1, RACK-2 | 1 to 5 | CKM00194401101 | Dell Unity Server (MLAN Storage) | No
67 | COMMS ROOM 1, RACK-3 | 41, 42 |  | uc6pnbmep002 | No | Retired, to be disposed
68 | COMMS ROOM 1, RACK-3 | 40 |  | RottadubDC05 | No | Retained till q1-2025
69 | COMMS ROOM 1, RACK-3 | 37,38, 39 |  | CCTV Fibre converter/Cable Run | No
70 | COMMS ROOM 1, RACK-3 | 36 |  | ROTTASWiSCSI117 | No | Retained till q1-2025
71 | COMMS ROOM 1, RACK-3 | 35 |  | ROTTASWiSCSI116 | No | Retained till q1-2025
72 | COMMS ROOM 1, RACK-3 | 33, 34 |  | ROTTADUBBI | No | Retained till q1-2025
73 | COMMS ROOM 1, RACK-3 | 31, 32 |  | ROTTADUBTEST | No | Retained till q1-2025
74 | COMMS ROOM 1, RACK-3 | 30 |  | Cable Tidy Panel 1U | No
75 | COMMS ROOM 1, RACK-3 | 28, 29 |  | Dell Unity Expansion Shelf | No
76 | COMMS ROOM 1, RACK-3 | 27 | 805201705700209 | IRE-C6DUB-IB | Yes | Movement AS-IS | Network 2, New server room Rack 07 | 26 | 805201705700209 | IRE-C6DUB-IB | Physical Verification needed
77 | COMMS ROOM 1, RACK-3 | 26 |  | Empty | No
78 | COMMS ROOM 1, RACK-3 | 25 |  | Cable Tidy Panel 1U | No
79 | COMMS ROOM 1, RACK-3 | 24 |  | Fiber Patch Panel | No
80 | COMMS ROOM 1, RACK-3 | 23 |  | Empty | No
81 | COMMS ROOM 1, RACK-3 | 22 |  | Empty | No
82 | COMMS ROOM 1, RACK-3 | 21 |  | Empty | No
83 | COMMS ROOM 1, RACK-3 | 20 |  | Gapped due to placement | No
84 | COMMS ROOM 1, RACK-3 | 19 | FDO2625M2AQ | IRE-C6DUB-MFG-COM1-SW1 | Yes | Movement AS-IS | Lan Rack, New server room Rack 10 | 21 | FDO2625M2AQ | IRE-C6DUB-MFG-COM1-SW1 | Physical Verification needed
85 | COMMS ROOM 1, RACK-3 | 18 |  | Cisco 4500-X | No | Retained till q1-2025
86 | COMMS ROOM 1, RACK-3 | 17 |  | Fiber Patch Panel | No
87 | COMMS ROOM 1, RACK-3 | 16 |  | Cisco 4500-X | No | Retained till q1-2025
88 | COMMS ROOM 1, RACK-3 | 15 |  | Cable Tidy Panel 1U | No
89 | COMMS ROOM 1, RACK-3 | 14 |  | HP Procurve 2810 48 | No | Retained till q1-2025
90 | COMMS ROOM 1, RACK-3 | 13 |  | Cable Tidy Panel 1U | No
91 | COMMS ROOM 1, RACK-3 | 12 |  | Fortigate 110C (RETIRED) | No
92 | COMMS ROOM 1, RACK-3 | 11 |  | FortiAnalyser 100C (RETIRED) | No
93 | COMMS ROOM 1, RACK-3 | 10 |  | Internet Fiber Line (RETIRED) | No
94 | COMMS ROOM 1, RACK-3 | 9 |  | Internet Router (RETIRED) | No
95 | COMMS ROOM 1, RACK-3 | 8 |  | HP Procurve 2810 DMZ (RETIRED) | No
96 | COMMS ROOM 1, RACK-3 | 7 |  | Fiber Patch Panel | No
97 | COMMS ROOM 1, RACK-3 | 6 |  | SonicWall SRA4200 (RETIRED) | No
98 | COMMS ROOM 1, RACK-3 | 5 |  | Fiber Patch Panel | No
99 | COMMS ROOM 1, RACK-3 | 4 |  | Fiber Patch Panel | No
100 | COMMS ROOM 1, RACK-3 | 3 |  | Fiber Patch Panel | No
101 | COMMS ROOM 1, RACK-3 | 2 |  | APC UPS 2U (RETIRED) | No
102 | COMMS ROOM 1, RACK-3 | 1 |  | APC UPS 2U (RETIRED) | No
103 | COMMS ROOM 1, RACK-4 | 41, 42 |  | Patch Panel 2U | No
104 | COMMS ROOM 1, RACK-4 | 40 |  | HP Procurve 2610 24 | No | Retained till q1-2025
105 | COMMS ROOM 1, RACK-4 | 38, 39 |  | Fiber Patch Panel | No
106 | COMMS ROOM 1, RACK-4 | 37 |  | Cable Tidy Panel 1U | No
107 | COMMS ROOM 1, RACK-4 | 35, 36 |  | Patch Panel 2U | No
108 | COMMS ROOM 1, RACK-4 | 34 |  | Patch Panel 1U | No
109 | COMMS ROOM 1, RACK-4 | 32, 33 |  | Patch Panel 2U | No
110 | COMMS ROOM 1, RACK-4 | 30, 31 |  | Patch Panel 2U | No
111 | COMMS ROOM 1, RACK-4 | 29 |  | Patch Panel 1U | No
112 | COMMS ROOM 1, RACK-4 | 28 |  | Patch Panel 1U | No
113 | COMMS ROOM 1, RACK-4 | 27 |  | Patch Panel 1U | No
114 | COMMS ROOM 1, RACK-4 | 26 |  | Patch Panel 1U | No
115 | COMMS ROOM 1, RACK-4 | 25 |  | Patch Panel 1U | No
116 | COMMS ROOM 1, RACK-4 | 24 | FDO2136E1L3 | IRE-DUB-C6-LAN-SW1 | Yes | Movement AS-IS | Lan Rack, New server room Rack 10 | 18 | FDO2136E1L3 | IRE-DUB-C6-LAN-SW1 | Physical Verification needed
117 | COMMS ROOM 1, RACK-4 | 23 | FDO2202I1LC | IRE-DUB-C6-LAN-SW1 | Yes | Movement AS-IS | Lan Rack, New server room Rack 10 | 17 | FDO2202I1LC | IRE-DUB-C6-LAN-SW1 | Physical Verification needed
118 | COMMS ROOM 1, RACK-4 | 22 | FDO2038E1MJ | IRE-DUB-C6-LAN-SW1 | Yes | Movement AS-IS | Lan Rack, New server room Rack 10 | 14 | FDO2038E1MJ | IRE-DUB-C6-LAN-SW1 | Physical Verification needed
119 | COMMS ROOM 1, RACK-4 | 21 | FDO2041E2UJ | IRE-DUB-C6-LAN-SW1 | Yes | Movement AS-IS | Lan Rack, New server room Rack 10 | 13 | FDO2041E2UJ | IRE-DUB-C6-LAN-SW1 | Physical Verification needed
120 | COMMS ROOM 1, RACK-4 | 20 |  | Empty | No
121 | COMMS ROOM 1, RACK-4 | 19 |  | HP Procurve 2920 48 | No | Retained till q1-2025
122 | COMMS ROOM 1, RACK-4 | 18 |  | HP Procurve 2920 48 | No | Retained till q1-2025
123 | COMMS ROOM 1, RACK-4 | 17 |  | HP Procurve 2920 48 | No | Retained till q1-2025
124 | COMMS ROOM 1, RACK-4 | 16 |  | Fiber Patch Panel | No
125 | COMMS ROOM 1, RACK-4 | 14, 15 |  | Patch Panel 2U | No
126 | COMMS ROOM 1, RACK-4 | 13 |  | HP Procurve 2920 48 | No | Retained till q1-2025
127 | COMMS ROOM 1, RACK-4 | 12 |  | Patch Panel 1U | No
128 | COMMS ROOM 1, RACK-4 | 11 |  | Cable Tidy Panel 1U | No
129 | COMMS ROOM 1, RACK-4 | 10 |  | Patch Panel 1U | No
130 | COMMS ROOM 1, RACK-4 | 9 |  | Patch Panel 1U | No
131 | COMMS ROOM 1, RACK-4 | 8 |  | Patch Panel 1U | No
132 | COMMS ROOM 1, RACK-4 | 7 |  | Patch Panel 1U | No
133 | COMMS ROOM 1, RACK-4 | 6 |  | Cable Tidy Panel 1U | No
134 | COMMS ROOM 1, RACK-4 | 5 |  | Patch Panel 1U | No
135 | COMMS ROOM 1, RACK-4 | 4 |  | Patch Panel 1U | No
136 | COMMS ROOM 1, RACK-4 | 2, 3 |  | APC UPS 2U (RETIRED) | No
137 | COMMS ROOM 1, RACK-4 | 1 |  | Empty/Cable Run | No
138 | COMMS ROOM 1, RACK-5 | 41,42 | 16201041110 | IRE-C6DUBL-MFG-FW | Yes | Movement AS-IS | Network 1, New server room Rack 08 | 21, 22 | 16201041110 | IRE-C6DUBL-MFG-FW | Physical Verification needed
139 | COMMS ROOM 1, RACK-5 | 40
140 | COMMS ROOM 1, RACK-5 | 38, 39 | 16201041413 | IRE-C6DUBL-MFG-FW-F | Yes | Movement AS-IS | Network 2, New server room Rack 07 | 21, 22 | 16201041413 | IRE-C6DUBL-MFG-FW-F | Physical Verification needed
141 | COMMS ROOM 1, RACK-5 | 37
142 | COMMS ROOM 1, RACK-5 | 36
143 | COMMS ROOM 1, RACK-5 | 35
144 | COMMS ROOM 1, RACK-5 | 34
145 | COMMS ROOM 1, RACK-5 | 33
146 | COMMS ROOM 1, RACK-5 | 32
147 | COMMS ROOM 1, RACK-5 | 31
148 | COMMS ROOM 1, RACK-5 | 30
149 | COMMS ROOM 1, RACK-5 | 29 | JPG2249001G | sc6sansw001 | No | replacement | Rack 6 | 39 | JPG2249001G | sc6sansw001
150 | COMMS ROOM 1, RACK-5 | 28 | JPG2249008J | sc6sansw002 | No | replacement | Rack 5 | 39 | JPG2249008J | sc6sansw002
151 | COMMS ROOM 1, RACK-5 | 27
152 | COMMS ROOM 1, RACK-5 | 25, 26 | DE600213144757 | sc6dd001 | Yes | Movement AS-IS | Platform 2, New Server Room - Rack 05 | 29, 30 | DE600213144757 | sc6dd001 | Physical Verification needed
153 | COMMS ROOM 1, RACK-5 | 24 |  |  | No
154 | COMMS ROOM 1, RACK-5 | 23 |  |  | No
155 | COMMS ROOM 1, RACK-5 | 21, 22 | D31SYP3 | uc6pnbmep003 | Yes | Movement AS-IS |  |  | D31SYP3 | uc6pnbmep003 | Physical Verification needed
156 | COMMS ROOM 1, RACK-5 | 19, 20 | H31SYP3 | ec6rr0u15.myl.com | Yes | post observation | Platform 2, New Server Room - Rack 05 | 14,15 | H31SYP3 | ec6rr0u15.myl.com | Physical Verification needed
157 | COMMS ROOM 1, RACK-5 | 17, 18 | J31SYP3 | ec6rr0u13.myl.com | Yes | post observation | Platform 2, New Server Room - Rack 05 | 12, 13 | J31SYP3 | ec6rr0u13.myl.com | Physical Verification needed
158 | COMMS ROOM 1, RACK-5 | 15, 16 | 141SYP3 | ec6rr0u11.myl.com | Yes | post observation | Platform 2, New Server Room - Rack 05 | 11, 12 | 141SYP3 | ec6rr0u11.myl.com | Physical Verification needed
159 | COMMS ROOM 1, RACK-5 | 13, 14 | F31SYP3 | ec6rr0u19.myl.com | Yes | post observation | Platform 1, New Server Room - Rack 06 | 18, 19 | F31SYP3 | ec6rr0u19.myl.com | Physical Verification needed
160 | COMMS ROOM 1, RACK-5 | 11, 12 | G31SYP3 | ec6rr0u17.myl.com | Yes | post observation | Platform 1, New Server Room - Rack 06 | 16, 17 | G31SYP3 | ec6rr0u17.myl.com | Physical Verification needed
161 | COMMS ROOM 1, RACK-5
162 | COMMS ROOM 1, RACK-5 | 9
163 | COMMS ROOM 1, RACK-5 | 8
164 | COMMS ROOM 1, RACK-5 | 7
165 | COMMS ROOM 1, RACK-5 | 6
166 | COMMS ROOM 1, RACK-5 | 5
167 | COMMS ROOM 1, RACK-5 | 4 | 952125002480, 952125002053 | nC6clst002 | Yes | post observation | Platform 1, New Server Room - Rack 06 | 29, 30 | 952125002480, 952125002053 | nC6clst002 | Physical Verification needed
168 | COMMS ROOM 1, RACK-5 | 2,3 |  | NetApp Storage 224C (Disk Shelf) | Yes | post observation | Platform 1, New Server Room - Rack 06 | 25, 26, 27, 28 |  |  | Physical Verification needed