## Solution
3J-Milan Site Office Movement
Sl.No | Area | Activity | Start Date | End Date | Activity Owner | Status | Dependency | Remarks
1 | Facility Services | MDF(3->7F) and IDF (6-> 8F) Rooms Readiness | 2024-08-01 | 2025-03-01 | Rui Rosa/ Site Team | Pending | 0 | TBD
2 | Facility Services | Power, UPS installtion and testing | 2025-03-01 | 2025-03-02 | Rui Rosa/ Site Team | Pending | 1 | TBD
3 | Facility Services | Cooling/HVAC system Procurement, Installation & testing | 2024-08-01 | 2025-03-02 | Rui Rosa/ Site Team | Pending | 1,2 | TBD
4 | Facility Services | Fiber cables Installation Between both IDF/MDF | 2024-08-01 | 2025-04-04 | Rui Rosa/ Site Team | Pending | 1 | TBD
5 | Facility Services | Copper Cable distribution from IDF to workstations | 2024-08-01 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 1 | TBD
6 | Facility Services | Fiber Testing Between MDF & IDF | 2025-03-02 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 2,3 | TBD
7 | Facility Services | Copper cables installations all areas | 2024-08-01 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 2,3 | TBD
8 | Facility Services | Rack, PDU, PP, Sensors and Monitoring Installations | 2025-03-02 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 2 | TBD
9 | Facility Services | Rack, PDU, PP, Sensors Validation and Testing(Watchdog) | 2025-03-05 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 2 | TBD
10 | Facility Services | SFP/Patch Cords(Fiber/Ethernet) Procurement | 2025-03-01 | 2025-04-05 | Rui Rosa/ Site Team | Pending | NA | TBD
11 | Facility Services | Earth Testing | 2025-03-05 | 2025-04-05 | Rui Rosa/ Site Team | Pending | 2 | TBD
12 | Facility Services | Heat Mapping for Wireless devices(AP) | 2025-03-01 | 2025-04-05 | Rui Rosa/ Site Team | Pending |  | TBD
13 | Network Services | Initiate of SDWAN Procurement for Site | 2024-08-01 | 2025-03-02 | Suresh / Ashwin | Pending | ISP | ISP to be confirmed
14 | Network Services | Initiate of Additional AP Procurement | 2024-08-01 | 2025-03-02 | Suresh / Ashwin | Pending | ISP | Procurement
15 | Network Services | SDWAN deployment and testing | 2025-04-03 | 2025-04-04 | Suresh / Ashwin | Pending | ISP | Yet to get the timelines
16 | Network Services | Existing Rack Elevation, review, approval | 2025-04-04 | 2025-04-05 | Suresh / Ashwin | Pending | NA | Final Rack Layout to be confirmed
17 | Network Services | Existing Switch Port Mapping Sheet Finalization | 2025-04-03 | 2025-04-04 | Suresh / Ashwin | Pending | NA
18 | Network Services | Cable Labeling, review and approval | 2025-04-03 | 2025-04-06 | Suresh / Ashwin | Pending | 1,5
19 | Facility Services | Wireless AP Deployment | 2025-04-05 | 2025-04-08 | Rui Rosa/ Site Team | Pending
20 | Facility Services | Power Testing at New DC | 2025-04-06 | 2024-04-07 | Rui Rosa/ Site Team | Pending | 8
21 | Facility Services | Cooling Testing at New DC | 2025-04-06 | 2024-04-08 | Rui Rosa/ Site Team | Pending | 8
22 | Facility Services | Fiber cables testing at New DC | 2024-04-08 | 2024-04-08 | Rui Rosa/ Site Team | Pending | 7
23 | Facility Services | Environmental Testing Monitoring | 2024-04-08 | 2024-04-08 | Rui Rosa/ Site Team | Pending | 9
24 | Facility Services | Earth Testing | 2024-04-08 | 2024-04-08 | Rui Rosa/ Site Team | Pending | 9
25 | Platform Services | Backup of all Servers- | TBD | TBD | IT Operations | TBC
26 | Platform Services | Device maintannce mode | TBD | TBD | IT Operations | TBC | 22
27 | Platform Services | Shutdown devices | TBD | TBD | IT Operations | TBC | 23
28 | Network Services | Shutdown network devices in order | TBD | TBD | Network Operations | TBC | 24
29 | Shifting Services | Dismounting and packing of all devices | TBD | TBD | Rui Rosa/ Site Team |  | 25
30 | Shifting Services | Shifting of all devices | TBD | TBD | Rui Rosa/ Site Team |  | 26
31 | Facility Services | Handover to shifting Team | TBD | TBD | Rui Rosa/ Site Team
32 | Facility Services | Rack & Stack of Routers | TBD | TBD | Rui Rosa/ Site Team
33 | Facility Services | Rack & Stack of CORE Switches | TBD | TBD | Rui Rosa/ Site Team
34 | Facility Services | Rack & stack of Access Switches | TBD | TBD | Rui Rosa/ Site Team
35 | Facility Services | Rack & Stack of Wireless Controller | TBD | TBD | Rui Rosa/ Site Team
36 | Facility Services | Rack & Stack of Servers | TBD | TBD | Rui Rosa/ Site Team
37 | Network Services | Establishment of SDWAN | TBD | TBD | Rui Rosa/ Site Team
38 | Network Services | Uplink Establishment of MGMT switch | TBD | TBD | Suresh / Ashwin
39 | Network Services | Establishment of Wireless Lan controller | TBD | TBD | Suresh / Ashwin
40 | Platform Services | Power up Servers | TBD | TBD | Senthil/Prabhu
41 | Network Services | Infoblox Movement to new MDF | TBD | TBD | Rui Rosa/ Site Team
42 | Facility Services | Validation of services | TBD | TBD | Rui Rosa/ Site Team
43 | Network Services | Secondary WAN Link Establishment | TBD | TBD | ISP
44 | Facility Services | Business Service Validation | TBD | TBD | Rui Rosa/ Site Team
45 | Project Team | Documentation and sign off | TBD | TBD | Rui Rosa/ Site Team