## Virtual Server Checklist
Virtual Server Transition Responsible Teams | Resource Information | Details - MFG | Resource Information
Transition Checklist Prepared and Filled by (Build Team) |  | Keshavamurti Vadavi
Transition Checklist Reviewed by (Wintel RUN Team - L1 and L2)
Transition Checklist Peer Reviewed by (Wintel RUN Team L2 and L3)
Transition Checklist Closed by (Wintel RUN Team - L1 and L2)
Virtual Server Checklist |  | Details | Artifacts Required
SR request Number | RITM4922097 | RITM4922097 | No
Change Number | RITM4939376 | RITM4939376 | No
Location Details | 6O-IDC | 6O-IDC | Yes
vCenter Name | 6ovcsa002 | 6ovcsa002 | Yes
Cluster Name | 6OWAPPNPRD001 | 6OWAPPNPRD001 | Yes
Vmware VC Level
a) Mandatory Hot Plug & Hot Add Except: 2003 OS (Yes/No) | Yes | Yes | Yes
b) Datastore Under Provisioned (Deploy VM in DataStore not in DS-Cluster) |  | 6O_6OWAPPNPRD001_1_00090-PMAX8K001 | Yes
c) VM HDD type (Select Yes/No) |  | Yes | Yes
i. Thin Provisioned |  | N/A
ii. Thick eager zeroed Provisioned (Default) |  | Yes
iii. RDM (Need Justification) |  | N/A
d) Datastore Type (NFS/VMFS 5/VMFS6) |  | VMFS 6 | Yes
e) Remove USB Controller |  | N/A | Yes
Server Basic Level Checklist
Server name as per standard |  | Script | No
Server Environment (Prod,QA,Test,Dev) |  | Prod | No
Application Details - Mandatory |  | ServiceNow - Sandbox | Yes
Application Owner Details - Mandatory
a. Primary Contact |  | Vetriselva Devendiran
b. Secondary Contact |  | Ashok Kumar Sahoo
Operating System & Service Pack |  | Script | Yes
Local admin credentials should be as per standards |  | Script | No
CPU Info & RAM Info |  | Script | Yes
No of sockets and cores (no of cores should be less then sockets) |  | Script | Yes
Pagefile Configuration |  | Script | Yes
IP Address details (IP, Subnet & Gateway) |  | Script | Yes
TimeZone |  | Script | Yes
DNS Server Name |  | Script
Primary DNS |  | Script
Secondary DNS |  | Script
DNS Suffix |  | Script | Yes
Verify 'A' Record Forward & Reverse Lookup (Yes/No) |  | Script | Yes
OS Level Mandatory Details (Verify SNOW Alerts if any Clear before )
OS License Activation |  | Script | Yes
Verify CAL licenses (Per User/Device) If yes need justify Mandatory |  | Script | Yes
Disk Space Details (Min. 30% free space as per Build Std.) |  | Script | Yes
CD ROM Drive Letter |  | Script | Yes
Local User Accounts |  | Script | Yes
Local 'Administrators' Group Members |  | Script | Yes
Local 'Remote Desktop Users' Group Members |  | Script | Yes
Remote Desktop Status |  | Script | Yes
Desktop Experience Feature Status |  | N/A | Yes
AutoUpdate Status |  | Script | Yes
Computer Object OU |  | Script | Yes
Server reporting to BigFix |  | Yes | Yes
Symantec Endpoint Protection Client status with version |  | Script | Yes
Any Affinity rule is deployed for the server? |  | No | Yes
Required Tools & Version
CrowdStrike |  | Script | Yes
IBM Endpoint Manager Client with version |  | Script | Yes
IBM BigFix Client with version |  | Script | Yes
SCOM Agent |  | Script | Yes
Qualys Agent
Installed Software |  | Script | Yes
Updated VM Hardware version (21) or Current Hardware Version applicable for the ESXi Host version |  | 21 | Yes
Updated Vmware Tool Version (12.4.5) |  | Script | Yes
DR Protection required (yes/no)
VM moved to DR Protected Datastores |  | No | Yes
VM configured for DR Protection |  | No | Yes
Service now
Screenshot of CI name, location, Owner, Group, Sub Group, L2 support group, CI upstream, Downstream and Service CI mapping |  | N/A | Yes
Post-Build Requirement
Installed Application Name: |  | N/A | Yes
Installed Windows Roles/Features Name: |  | N/A | Yes

## Formula Validation (hidden)
7G-EPD | W07VC001 | Dev | Yes
0N-STA | W0BVC001 | Prod | No
E2-ISTMFG | 22-SA40010 | POC
6Z-India Global Center | 23-SA40210 | QA
0B-GDC | WB5VC001 | Test
07-DR | 0bvcsa001 | SANDBOX
6X-Hosur | 3NVCENTER1
CL-RUSSIA | 3NVMOSA2
5E-BUDAPEST | 6ovcsa002.myl.com
6Y-GBS-Hyderabad | b5vcsa001.myl.com
Sydney | EZVCSA001
6E-Hyderabad | W0BVCPOC001
BG-TROISDORF | W6EVC001
2Q-FRANCE | W6VVC001
07-MGW
0H-SGRLND
0N-STA
0P-PR
0R-SPE
0S-GSO
0U-RCKFRD
0Y-SanCarlos
1K-DPTLABS
1L-SanAntonio
1L-SanAntonioMFG
23-Brisbane
23-BRISBANE
2F-CAN
2J-CAMPOS
2K- SAO-PAULO
2K-RIO
3B-GALWAY
3D-IRL
3D-IRL
3D-IRL
3D-IRL-1
51-New Zealand
59-POLAND
5D-HUNGARY
65-UK
65-UK
68-VISAKHAPATNAM
69-VIZIANAGARAM
6B-Nashik
6B-Nashik
6G-ASTRIX
6H-Bollaram
6J-AURANGABAD
6J-Aurangabad
6O-IDC
6P-PARAWADA SEZ
6S-OSD6
6T-INDORE
6T-Indore
6W-BOMMASANDRA
6W-Bommasandra
6X-Hosur
7G-EPD
90-Sarigam
91-Ahmedabad
95-Bangalore R&D
B5-FRANKFURT
Beijing
BG-TROISDORF
C1-CONFIENZA
C1-CONFIENZA
C6-DUBLIN
C6-DUBLIN
CI-MERIGNAC
CI-MERIGNAC
E0-ALGERIA
E1-CAIRO
E1-CAIRO
E2-ISTMFG
E3-ISTDC
E4-VEGABAJA
E4-VEGABAJA
E5-BARC
E5-BARC
E6-LITTLE ISLAND
E6-LITTLE ISLAND
E7-Dalian
E7-Dalian
eu-central-1
EZ-SHG
Osaka
POC-DC
Tokyo
us-east-1